## WBS
VitalFit Supplements — Spring Launch WBS
Client: VitalFit ¦ Budget: $400K ¦ Duration: 10 weeks ¦ Channels: Meta, TikTok, Google Search, Connected TV
Phase 1: Setup (Weeks 1-3)
Task | Owner | Duration | Dependencies | Notes
Client kickoff call | Sarah (Account Lead) | Week 1 | — | First engagement — set expectations on CTV measurement, creative timelines, and legal review process
Receive brand assets & guidelines | Sarah (Account Lead) | Week 1 | Kickoff call | [FLAG] Creative is from external agency we haven't worked with — confirm asset specs and handoff process at kickoff
Audience research & persona development | Anika (Insights) | Week 1-2 | Kickoff call | New client — essential for targeting across 4 channels. Inform TikTok creator strategy
[FLAG] Legal review of supplement ad claims | Sarah (Account Lead) + Client Legal | Week 1-2 | Kickoff call | NEW STEP — no precedent in past projects. Supplement claims must be cleared before any copy goes live. Start early to avoid blocking launch
Build media plan | Jordan (Planner) | Week 1-3 | Kickoff call; Audience research | 4 channels = 3-week build (matches GlowUp pattern). Heavy TikTok allocation (50% / ~$200K) needs dedicated planning
[FLAG] TikTok creator sourcing & briefing | Jordan (Planner) + External Creative | Week 2-3 | Media plan (draft); Legal review | NEW STEP. 50% of budget is creator-driven TikTok — need creator selection, briefing, and content calendar. No past project had this scale of creator work
[FLAG] CTV inventory & deal setup | Marcus (Programmatic Lead) | Week 2-3 | Media plan (draft) | NEW CHANNEL. Agency hasn't run CTV for DTC before. Marcus to source inventory, negotiate CPMs, and define targeting. Build in extra buffer
[FLAG] CTV measurement & attribution setup | Marcus (Programmatic Lead) + Anika (Insights) | Week 2-3 | CTV deal setup | NEW STEP. Client nervous about CTV measurement — define KPIs, attribution methodology, and reporting approach before launch
Trafficking & tagging (all platforms) | Priya (Ad Ops) | Week 3 | Media plan; Legal review; Brand assets | 4 platforms — full week needed (matches GlowUp). Legal-approved copy required before trafficking
Phase 2: Launch (Weeks 4-5)
Task | Owner | Duration | Dependencies | Notes
Phased launch: Meta + Google Search | Jordan (Planner) + Priya (Ad Ops) | Week 4 | Trafficking & tagging | Lead with proven channels first (matches GlowUp staggered approach)
TikTok launch (creator content) | Jordan (Planner) + Priya (Ad Ops) | Week 5 | Phased launch; Creator content ready | Stagger by 1 week to QA creator assets and manage pacing on largest budget line
[FLAG] CTV launch | Marcus (Programmatic Lead) + Priya (Ad Ops) | Week 5 | CTV deal setup; Trafficking | Launch alongside TikTok. Treat as test — start with conservative pacing and scale based on early signals
Phase 3: Optimize (Weeks 4-9)
Task | Owner | Duration | Dependencies | Notes
Weekly performance reviews | Jordan (Planner) | Weeks 4-9 | Campaign launch | Include CTV metrics even if early data is thin — client will want visibility
[FLAG] CTV early-read report | Marcus (Programmatic Lead) + Anika (Insights) | Week 6 | 2 weeks of CTV data | NEW STEP. Client is nervous about CTV — provide a dedicated early read with go/no-go recommendation before mid-flight
Mid-flight optimization report | Jordan (Planner) + Anika (Insights) | Week 7 | Weekly reviews | Full cross-channel view. Assess CAC vs. targets ($18 Meta, $22 TikTok). Recommend budget shifts if needed
Creative refresh (Meta + TikTok) | External Creative + Jordan (Planner) | Week 7 | Mid-flight report | [FLAG] External creative agency — build in extra lead time. Request refreshed assets by Week 6 to launch Week 7
Audience & budget rebalancing | Jordan (Planner) | Week 7-8 | Mid-flight report | Expect potential shift between TikTok and CTV based on performance. GlowUp shifted Display to TikTok at this stage
Phase 4: Wrap (Weeks 9-11)
Task | Owner | Duration | Dependencies | Notes
Final performance report | Jordan (Planner) + Anika (Insights) | Week 10 | All campaigns complete | Include CTV learnings section — this will be the agency's first DTC CTV case study
Vendor reconciliation | Finance + Marcus (Programmatic Lead) | Week 10-11 | Final report | 4 vendors + new CTV partner = higher reconciliation complexity. FreshBrew took an extra week on Meta alone — budget 2 weeks
Client debrief + next steps | Sarah (Account Lead) + Jordan (Planner) | Week 11 | Final report; Vendor reconciliation | Include CTV test results and recommendation for future investment. New client — use debrief to build relationship for renewal
Uncertainty Flags
Flag | Risk | Mitigation
CTV is brand new for the agency (DTC context) | No internal benchmarks for pacing, CPMs, or attribution. Marcus is capable but flying without a playbook |  | Start conservative, build a dedicated CTV early-read checkpoint at Week 6, and document everything for future projects
External creative agency (unknown partner) | Asset delays, format mismatches, or misaligned creative quality — FreshBrew had a 2-day delay with an internal creative partner |  | Establish asset specs + delivery SLA at kickoff. Request creative refresh assets 1 week before needed. Sarah to own the relationship
Legal review for supplement claims | Entirely new compliance step — could block ad copy and delay trafficking if not started early |  | Begin legal review in Week 1 in parallel with audience research. Don't let it become a Week 3 bottleneck
TikTok at 50% of budget ($200K) — creator-driven | Past TikTok work (GlowUp) was not creator-heavy. Creator sourcing, briefing, and content approval is a different workflow |  | Dedicate planning time in Weeks 2-3. Jordan should own a creator content calendar separate from the media plan
Aggressive CAC targets ($18 Meta / $22 TikTok) | No historical data from this client. DTC supplements is a competitive category |  | Set expectations at kickoff that Weeks 4-5 are a learning phase. Mid-flight report should include a realistic CAC trajectory, not just a snapshot
CTV measurement / attribution | Client is already nervous. If reporting is unclear, trust erodes on a channel that's eating budget |  | Define measurement methodology before launch (Week 2-3). Anika and Marcus co-own this. Present it to the client before go-live

## Gantt Chart
VitalFit Supplements — Gantt Chart (10 Weeks + Wrap)
Budget: $400K ¦ Channels: Meta, TikTok, Google Search, Connected TV ¦ Yellow rows = deviation flags
Task | Owner | Phase | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11
Phase 1: Setup (Weeks 1-3)
Client kickoff call | Sarah | Setup | ●
Receive brand assets & guidelines | Sarah | Setup | ●
Audience research & persona development | Anika | Setup | ◄ | ►
Legal review of supplement ad claims | Sarah + Legal | Setup | ◄ | ►
Build media plan | Jordan | Setup | ◄ | ■ | ►
TikTok creator sourcing & briefing | Jordan + Creative | Setup |  | ◄ | ►
CTV inventory & deal setup | Marcus | Setup |  | ◄ | ►
CTV measurement & attribution setup | Marcus + Anika | Setup |  | ◄ | ►
Trafficking & tagging (all platforms) | Priya | Setup |  |  | ●
Phase 2: Launch (Weeks 4-5)
Phased launch: Meta + Google Search | Jordan + Priya | Launch |  |  |  | ●
TikTok launch (creator content) | Jordan + Priya | Launch |  |  |  |  | ●
CTV launch | Marcus + Priya | Launch |  |  |  |  | ●
Phase 3: Optimize (Weeks 4-9)
Weekly performance reviews | Jordan | Optimize |  |  |  | ◄ | ■ | ■ | ■ | ■ | ►
CTV early-read report | Marcus + Anika | Optimize | [5 empty] | ●
Mid-flight optimization report | Jordan + Anika | Optimize | [6 empty] | ●
Creative refresh (Meta + TikTok) | External + Jordan | Optimize | [6 empty] | ●
Audience & budget rebalancing | Jordan | Optimize | [6 empty] | ◄ | ►
Phase 4: Wrap (Weeks 9-11)
Final performance report | Jordan + Anika | Wrap | [9 empty] | ●
Vendor reconciliation | Finance + Marcus | Wrap | [9 empty] | ◄ | ►
Client debrief + next steps | Sarah + Jordan | Wrap | [10 empty] | ●
Legend
Setup
Launch
Optimize
Wrap
Deviation Flag